# Principal Investigator Role Description and Tender Specification

## Theorising Ways of Knowing in Religious Education

# Invitation to Tender

## Principal Investigator: Theorising Ways of Knowing in Religious Education

### 1. Project Title

Theorising Ways of Knowing in Religious Education

### 2. Lead Organisation

This project is led by The Religious Education Council of England and Wales, a registered charity and company limited by guarantee; the concept note identifies the organisation as Charity Commission England Ref No. 1116543 and Company Ref No. 5907308.

### 3. Background and Purpose of the Project

The Religious Education Council of England and Wales invites tenders for a Principal Investigator to provide senior intellectual, methodological and research leadership for a proposed 24-month Templeton World Charity Foundation research project, Theorising Ways of Knowing in Religious Education.

The project seeks to develop a rigorous theoretical framework for understanding “ways of knowing” in Religious Education. It builds on previous Templeton World Charity Foundation Big Questions in Classroom projects and addresses a significant gap in Religious Education: while current curriculum developments recognise that RE draws on multiple disciplines and involves “ways of knowing and reasoning”, there is not yet a coherent theoretical account of what these disciplinary forms of knowledge are, how they relate to one another, or what it means for pupils to become proficient in them.

The project focuses on four foundational disciplines - theology, philosophy, history and the human/social sciences - and seeks to identify their core intellectual structures, the ways in which they contribute to understanding religion and worldviews, and how they support meaning-making and civic life.

The project is designed to bridge scholarly rigour and practical relevance. It will be led by the Religious Education Council of England and Wales and will draw on partnerships across universities, schools, and religion and belief communities. The Principal Investigator will play a central role in ensuring that the project produces a high-quality interdisciplinary theory of disciplinary knowledge in RE and that this theory is translated into usable outputs for academics, curriculum designers, teachers, policymakers and the wider RE/RW sector.

Important Note: This appointment is subject to confirmation of funding from a Charitable Foundation and final contractual agreement.

## 4. Purpose of the Principal Investigator Role

The Principal Investigator will provide intellectual and research leadership for the project. The role holder will be responsible for shaping and overseeing the theoretical framework, ensuring methodological coherence across the research programme, guiding the work of the research team, and supporting the delivery of high-quality academic, applied and public-facing outputs.

The Principal Investigator role is envisaged as the senior research leadership role within the project: accountable for scholarly quality, coherence of research design, theoretical development, and the integration of findings across the project’s academic, empirical and practical strands.

The role is open to either:

- a university-based academic, for example through institutional buy-out or fractional appointment; or

- an independent researcher, consultant or research organisation with the necessary scholarly expertise, capacity, and university affiliation.

A single Principal Investigator is preferred. However, applications from two Co-Investigators proposing a clear joint leadership model will also be considered, provided the proposal sets out how responsibilities, accountability, intellectual leadership and delivery will be shared.

## 5. Core Research Questions

The Principal Investigator will lead the project in addressing the four core questions identified in the concept note:

- What are the disciplinary building blocks in a religion and worldviews curriculum?
This includes identifying the conceptual, methodological and epistemic foundations of theology, philosophy, history and the human/social sciences as they relate to Religious Education.

- How do pupils develop disciplinary knowledge over time?
The project will examine progression from early encounters with stories, artefacts and lived experience to more advanced forms of reasoning, including the evaluation of contested claims.

- What are the end goals for pupils in disciplinary knowledge?
The funding proposal identifies possible starting points including epistemic discernment, disciplinary fluency, judgement and evaluation, and reflexive and responsible knowing.

Supplementary Question, but not a project focus: How does disciplinary knowledge in RE contribute to human flourishing and civic responsibility?
The project may explore epistemic humility, dialogue across difference and meaning-making in relation to individual development and societal cohesion as this arises from the research.

## 6. Key Responsibilities

The appointed Principal Investigator will be expected to undertake the following responsibilities.

### A. Intellectual and Theoretical Leadership

- Lead the development of a rigorous interdisciplinary theory of “ways of knowing” in Religious Education.

- Provide conceptual clarity on how theology, philosophy, history and the social sciences contribute distinctively to knowledge formation, interpretation, reasoning and evaluation in RE.

- Develop a coherent account of disciplinary progression and epistemic development across ages 5–16, in line with the project’s theory-building ambition.

- Ensure that the emerging theoretical framework is both academically robust and practically meaningful for curriculum design, teacher development and policy discussion.

### B. Research Design and Methodological Oversight

- Refine and oversee the project’s four-stage interdisciplinary research design: epistemic analysis, curriculum mapping, empirical school-based case studies, and theory building.

- Ensure that research questions, methods, data sources, analysis and outputs remain coherent across all phases of the project.

- Oversee the development of research instruments, sampling strategies, ethical procedures and analytical frameworks.

- Ensure appropriate standards of research ethics, safeguarding and consent are adhered to.

- Support the design and interpretation of empirical case studies in diverse school settings, including how pupils develop disciplinary knowledge in practice.

### C. Team Leadership and Management

- Provide research leadership for the wider project team, expected to include a Co-Investigator Adviser (0.2 FTE, likely consultancy basis), Co-Investigator Teacher/Practitioner (0.2 FTE likely secondment), a postdoctoral researcher (0.5FTE), practitioner partners and advisory or reference groups.

- Supervise and mentor the postdoctoral researcher in relation to literature review, empirical design, data collection, analysis, writing and publication.

- Work constructively with practitioner partners and advisers, ensuring that teacher and school-based perspectives inform the development of the framework.

- If applying as two Co-Investigators, provide a clear model for shared leadership, including named responsibilities, decision-making arrangements, allocation of time and continuity of accountability.

### D. Stakeholder and Advisory Engagement

- Work with the Religious Education Council of England and Wales, the Project Director and any steering or advisory structures established for the project.

- Contribute to the design and facilitation of reference or focus group activity involving academic and specialist disciplinary voices, religion and belief communities, and teachers.

- Engage sensitively and productively with universities, schools, teachers, religion and belief communities and wider RE/RW stakeholders.

- Help ensure that the project maintains a strong bridge between theoretical development and educational practice

### E. Analysis, Synthesis and Outputs

- Lead the synthesis of findings from epistemic analysis, curriculum mapping, empirical case studies and stakeholder engagement.

- Produce or oversee the production of a framework of disciplinary building blocks for curriculum design.

- Produce or oversee the production of a model of epistemic end goals and progression for primary and secondary phases.

- Contribute substantially to academic outputs, including journal articles and a major monograph provisionally titled Ways of Knowing in Religious Education.

- Support the development of teacher guidance materials and practitioner-facing resources.

- Contribute to public and policy outputs, including a policy briefing on disciplinary knowledge in RE and its value for civic society.

### F. Reporting, Governance and Grant Management

- Provide regular research updates to the Project Director, the Religious Education Council of England and Wales, and relevant steering or advisory groups.

- Contribute to funder reporting, including progress narratives, milestone updates, evidence of outputs and impact, and any required final reporting.

- Support project planning, risk identification, quality assurance and budget-aware delivery of the research programme.

- Work within agreed governance, procurement, safeguarding, data protection and research ethics requirements.

### G. Dissemination and Sector Impact

- Represent the project at academic conferences, sector events, webinars, roundtables and policy or practitioner forums.

- Support international conference symposia, open access publication planning and dissemination activity, consistent with the outputs and dissemination budget lines in the concept note.

- Communicate complex theoretical ideas clearly to different audiences, including academics, teachers, curriculum designers, policymakers and religion/belief community stakeholders.

- Ensure that the project contributes to the anticipated intellectual, educational and societal impact: a new interdisciplinary theory of knowledge in RE; improved clarity for teachers and curriculum designers; and support for dialogue, epistemic resilience and responsible citizenship.

## 7. Required Skills and Experience

Applicants should demonstrate:

- Substantial expertise in Religious Education, Religion and Worldviews education, or a closely related field.

- Strong interdisciplinary knowledge relevant to the project’s focus on theology, philosophy, history and the human/social sciences.

- A track record of high-quality research and publication, including peer-reviewed publications or equivalent research outputs relevant to RE/RW, epistemology, curriculum, disciplinary knowledge, religious studies, theology, philosophy of education, education studies or related fields.

- Experience of leading complex research projects, including designing methodology, managing research quality, overseeing analysis and delivering outputs.

- Capacity to lead theory-building work, including conceptual synthesis across disciplines and translation of theory into practical frameworks.

- Knowledge of curriculum, pedagogy or progression in Religious Education, particularly in relation to disciplinary knowledge or “ways of knowing”.

- Experience of empirical research in education settings, including qualitative methods and/or school-based case study research.

- Understanding of ethics, safeguarding and consent procedures in education research

- Excellent writing, synthesis and communication skills, including the ability to write for academic, professional and policy audiences.

- Ability to work collaboratively with diverse stakeholders, including academics, teachers, school leaders, religion and belief communities, policymakers and charitable or sector bodies.

- Strong project management and delivery skills, including reliability, responsiveness and the ability to work within agreed timelines and budgets.

## 8. Desirable Skills and Experience

The following would be advantageous:

- Experience of leading funded research involving multiple institutional or sector partners.

- Experience supervising postdoctoral researchers, research associates, doctoral researchers or practitioner researchers.

- Experience working with advisory groups, reference groups or stakeholder panels.

- Knowledge of recent developments in RE/RW curriculum reform, disciplinary knowledge, curriculum progression and/or national curriculum debates.

- Experience producing practitioner resources, policy briefings, curriculum frameworks or teacher guidance materials.

- Experience disseminating research through conferences, webinars, roundtables, public engagement or professional learning events.

- Experience working across academic and non-academic settings, including schools, charities, professional associations or public bodies.

## 9. Expected Deliverables

The Principal Investigator will be expected to lead, contribute to or quality assure the following deliverables.

### Research Design and Project Infrastructure

- Inception and research design plan, including refined research questions, methodology, workplan, roles, governance, risk management and ethics route.

- Epistemic analysis framework, identifying the conceptual, methodological and epistemic foundations of the relevant disciplines.

- Curriculum mapping framework, analysing how disciplinary elements are sequenced and how progression is currently conceptualised.

### Theory Development and Empirical Synthesis

- Comparative map of ways of knowing across theology, philosophy, history and the human/social sciences.

- Case study analytical framework for examining pupil development of disciplinary knowledge in school settings.

- Interim synthesis papers or working papers to support project decision-making and stakeholder engagement.

- Final theoretical framework articulating disciplinary progression and epistemic development in RE across ages 5–16.

### Academic Outputs

- Contribution to a theory of disciplinary knowledge in RE grounded in four disciplines.

- Substantial contribution to the proposed monograph, Ways of Knowing in Religious Education.

- Contribution to journal articles in education, philosophy, theology or related fields.

- Contribution to international conference symposia or equivalent academic dissemination.

### Applied, Practitioner and Policy Outputs

- Framework of disciplinary building blocks for curriculum design.

- Model of epistemic end goals and progression for primary and secondary phases.

- Teacher guidance materials and/or practitioner-facing resources.

- Policy briefing on disciplinary knowledge in RE and its value for civic society.

- Contribution to national curriculum implementation discussions, if appropriate.

### Reporting and Dissemination

- Regular progress reports for the Project Director, project governance group and funder reporting.

- Contribution to final grant reporting and impact evidence.

- Presentations to relevant academic, teacher, policy and stakeholder audiences.

- Participation in project dissemination events, webinars, roundtables or conferences.

## 10. Indicative Time Commitment and Fee/FTE Expectation

The funding application identifies the Principal Investigator role as 0.2 FTE for 24 months. The proposed fee is £60,000. For tendering purposes, applicants should propose a costed model based on this level of commitment and budget, equivalent to approximately one day per week across the life of the project, with flexibility to vary the pattern of work across project phases.

The project duration is identified as 24 months, with an ideal start date of September 2027, although the start date may be flexible.

Applicants should provide a transparent costed proposal, including:

- proposed day rate, salary buy-out, consultancy fee or institutional FTE cost;

- number of days or FTE allocation proposed;

- any VAT, institutional on-costs or overheads;

- any assumptions about travel, meetings, supervision, dissemination or publication work;

- any alternative costed model if the applicant believes a different structure would better deliver the project.

Applicants proposing a joint Co-Investigator leadership model should provide a single combined costing and make clear how the 0.2 FTE equivalent, or any proposed alternative, would be divided.

Important Note: The final fee will be subject to funding confirmation, contractual agreement, value for money assessment and alignment with the agreed project budget.

## 11. Indicative Project Phases

Applicants are invited to propose their own workplan, but tenders should show how the Principal Investigator role will support the following broad phases.

| Phase | Indicative focus | Principal Investigator contribution |
| --- | --- | --- |
| Phase 1: Inception and design | Refine research design, governance, ethics, team roles and project plan | Lead intellectual framing; approve methodology; establish quality assurance |
| Phase 2: Epistemic analysis and curriculum mapping | Analyse disciplinary foundations and curriculum progression | Lead conceptual analysis; develop comparative map; guide literature and curriculum review |
| Phase 3: Empirical case study phase | Investigate how pupils develop disciplinary knowledge in practice | Oversee case study design, ethics, analysis and interpretation |
| Phase 4: Theory building and synthesis | Produce coherent account of disciplinary progression and epistemic development | Lead synthesis and framework development |
| Phase 5: Outputs and dissemination | Academic, practitioner and policy outputs | Lead or contribute to publications, guidance, briefings and dissemination |

## 12. Application Requirements

Applicants should submit:

- Covering letter of no more than two pages, setting out interest in the project and suitability for the role.

- Curriculum vitae for the proposed Principal Investigator, or CVs for both applicants in a joint Co-Investigator proposal.

- Research leadership statement of no more than four pages, outlining:

  - understanding of the project aims and research questions;

  - proposed approach to theoretical and methodological leadership;

  - approach to interdisciplinary working across theology, philosophy, history and human/social sciences;

  - approach to supervising or working with the postdoctoral researcher and wider project team;

  - approach to stakeholder engagement and dissemination.

- Relevant publications or outputs list, highlighting up to six outputs most relevant to this project.

- Costed proposal, including fee/FTE model, number of days, VAT/overheads where applicable, and any assumptions.

- Availability statement, including ability to begin around April 2027, subject to funding and final agreement.

- Joint leadership statement, if applying as two Co-Investigators, explaining the division of responsibilities, decision-making process, communication arrangements and single point of accountability.

Applications should be sent to chair@religiouseducationcouncil.org.uk by 30th September 2026.

Shortlisted applicants will be invited to an interview or informal conversation by Zoom or Teams. Interviews are expected to take place in early October.

## 13. Selection Criteria

Applications will be assessed against the following criteria.

| Criterion | Evidence sought | Suggested weighting |
| --- | --- | --- |
| Understanding of the project | Clear grasp of aims, research questions, TWCF alignment and RE/RW context | 20% |
| Intellectual and interdisciplinary expertise | Ability to lead theory-building across theology, philosophy, history and human/social sciences | 25% |
| Research design and methodological leadership | Capacity to oversee epistemic analysis, curriculum mapping, empirical case studies and synthesis | 15% |
| Leadership and team management | Experience leading research teams, supervising researchers and working with partners | 15% |
| Outputs and dissemination | Track record of academic publication and ability to produce practitioner and policy outputs | 15% |
| Value for money and deliverability | Transparent, realistic and proportionate costed proposal | 10% |

The Religious Education Council of England and Wales reserves the right not to appoint if no proposal meets the required standard or if funding is not confirmed.

## 14. Contracting Model

The appointment may be made through one of the following routes:

- contract with a university or higher education institution;

- consultancy contract with an independent researcher or research organisation which has affiliation to a university or higher education institution;

- joint contract or linked agreements for two Co-Investigators, subject to agreement on accountability and delivery.

The final contractual model will be agreed with the preferred applicant and will be subject to funding confirmation, procurement requirements, insurance, safeguarding, ethics, data protection and any funder conditions.

## 15. About the Project’s Intended Contribution

The project is distinctive in moving beyond curriculum design to theorising knowledge itself. It aims to offer a systematic account of the disciplinary foundations of RE, integrating theology, philosophy, history and social sciences within a single epistemic framework. Its anticipated outputs include academic theory-building, a major monograph, journal articles, international conference symposia, practical curriculum frameworks, teacher guidance materials, a policy briefing and contribution to national curriculum implementation where appropriate.

This role is therefore suited to a senior researcher who can combine intellectual ambition, interdisciplinary scholarship, education research expertise and practical commitment to the flourishing of high-quality Religious Education.

## 16. Informal Enquiries

Informal enquiries may be directed to chair@religiouseducationcouncil.org.uk

Please note that informal conversations are intended to support understanding of the tender and do not form part of the formal assessment process.

## 17. Equality, Diversity and Inclusion

The Religious Education Council of England and Wales welcomes applications from suitably qualified individuals and teams from a range of backgrounds, institutional settings and career pathways. Applications will be assessed on the published criteria above.

Joint applications are welcome where two Co-Investigators can demonstrate a coherent shared leadership model. A single Principal Investigator remains the preferred model where one applicant can demonstrate the full range of expertise, leadership and capacity required.